## Start here
MarketStreet ¦ Team tracker
Weekly contributions, source evidence, and leader review · Updated through October 25, 2026
Update one log. Keep every checkpoint clear.
Open the Weekly log
One row per member per week. Filter the Week column to find your checkpoint.
Check the work and evidence
Edit contributions and rating dropdowns. Add confirmed paired work, reviews, or testing done outside GitHub.
Confirm all six entries
Set Leader review to Confirmed after checking each row. Unverified entries need details before checkpoint sign-off.
Add the next checkpoint
Press Tab in the last table cell to add a row. Add six members for the new week, then copy an Overview week column and update its heading.
Contribution ratings
| Delivered | Attributable checkpoint deliverable in Git history.
| Supported | Attributable correction, refinement, or integration work.
| Unverified | No attributable checkpoint work located. Confirm with the member.
These are provisional assessments of repository evidence, not grades or attendance records. Unverified does not mean no work was done. Do not approve a checkpoint until the leader has checked all six entries.
Jump to the member-by-week overview

## Overview
Contributions at a glance
Click any rating to edit its log entry · Ratings describe repository evidence and remain provisional until reviewed
Backfilled: Weeks 3–6. Current coverage: Weeks 3–9. Amber cells need contribution details.
Member | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
Austin Tran Nguyen | Delivered | Delivered | Delivered | Delivered | Delivered | Unverified | Supported | Delivered
Sophia Musetti | Delivered | Supported | Delivered | Delivered | Unverified | Delivered | Delivered | Delivered
Arya Nair | Delivered | Unverified | Supported | Unverified | Unverified | Unverified | Unverified | Delivered
Benjamin Nguyen | Delivered | Supported | Unverified | Supported | Supported | Supported | Unverified | Delivered
Shayaan M. Dawra | Delivered | Unverified | Unverified | Unverified | Unverified | Unverified | Unverified | Delivered
Agah Duzenli | Delivered | Delivered | Delivered | Delivered | Delivered | Delivered | Unverified | Delivered
Leader-confirmed entries | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
Entries needing details | 0 | 2 | 2 | 2 | 3 | 3 | 4 | 0
Log entries recorded | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Delivered = attributable deliverable Supported = attributable supporting change Unverified = confirm with member
Add a future week: copy the last week column to the right, change its heading, and add six matching rows in Weekly log.

## Weekly log
Weekly contribution log
Edit this table each checkpoint · Six members per week · Confirm evidence before leader sign-off
Filter a week, update the six entries, then confirm. New rows: press Tab in the final table cell.
Week | Member | Contribution / deliverable | Evidence (commit IDs) | Contribution rating | Leader review
Week 3 | Austin Tran Nguyen | Created the trade data dictionary and project proposal; organized the foundation, requirements, and design documents. | 1211953, 4f1d5c4, 70cf2d0 | Delivered | Provisional
Week 3 | Sophia Musetti | Added the finalized transaction workflow diagram for the system-design exercise. | afe8c13 | Delivered | Provisional
Week 3 | Arya Nair | Added the workflow exception and failure paths. | 4c4e0da | Delivered | Provisional
Week 3 | Benjamin Nguyen | Wrote presentation, application-logic, and data-tier responsibility notes. | ad515aa, 0cdcf79 | Delivered | Provisional
Week 3 | Shayaan M. Dawra | Uploaded the architecture diagram for the system-design exercise. | 16b2f64 | Delivered | Provisional
Week 3 | Agah Duzenli | Added the state transition diagram, state definitions, and related transaction documentation. | 2763615 | Delivered | Provisional
Week 4 | Austin Tran Nguyen | Added the semantic transaction page and September 16 live-build HTML; corrected the class form location and CSS reference. | c148e95, 39be58c, 3855c7c | Delivered | Provisional
Week 4 | Sophia Musetti | Updated the transaction-form HTML and cleaned up its comments. | 2ddb1cd, ae3598b | Supported | Provisional
Week 4 | Arya Nair | No attributable repository change located for this checkpoint. Confirm any paired work, reviews, testing, or offline work before approving. | History reviewed through 2026-10-25 | Unverified | Needs details
Week 4 | Benjamin Nguyen | Refined form spacing and a button in the Week 4 form-label exercise. | 8015abe, 829536b | Supported | Provisional
Week 4 | Shayaan M. Dawra | No attributable repository change located for this checkpoint. Confirm any paired work, reviews, testing, or offline work before approving. | History reviewed through 2026-10-25 | Unverified | Needs details
Week 4 | Agah Duzenli | Added labeled email and password controls with a transaction-details fieldset; updated the transaction form. | 8081f7d, e54acc7 | Delivered | Provisional
Week 5 | Austin Tran Nguyen | Added the September 21 CSS styling and September 27 Milestone form with its stylesheet. | 9c0ce0f, bb499a5 | Delivered | Provisional
Week 5 | Sophia Musetti | Added the stock-trade form and CSS styling; refined the Milestone stylesheet. | e2c55ac, 401689b | Delivered | Provisional
Week 5 | Arya Nair | Added the individual expense-reimbursement form and responsive CSS. This records individual coursework; group-exercise participation needs confirmation. | 0856bff, 2dfd7ac | Supported | Provisional
Week 5 | Benjamin Nguyen | No attributable repository change located for this checkpoint. Confirm any paired work, reviews, testing, or offline work before approving. | History reviewed through 2026-10-25 | Unverified | Needs details
Week 5 | Shayaan M. Dawra | No attributable repository change located for this checkpoint. Confirm any paired work, reviews, testing, or offline work before approving. | History reviewed through 2026-10-25 | Unverified | Needs details
Week 5 | Agah Duzenli | Built the early trade UI and styled the checkpoint presentation. This UI work was committed September 30. | 15f1fe1 | Delivered | Provisional
Week 6 | Austin Tran Nguyen | Added the Week 6 HTML, CSS, and whole-share validation script; organized earlier exercises. Also added the individual Week 6 form. | 311563c | Delivered | Provisional
Week 6 | Sophia Musetti | Added whole-share quantity tests, live quantity feedback, and custom validity handling. Also added the individual Week 6 assignment. | 5d47986, 391308e, e988569 | Delivered | Provisional
Week 6 | Arya Nair | No attributable repository change located for this checkpoint. Confirm any paired work, reviews, testing, or offline work before approving. | History reviewed through 2026-10-25 | Unverified | Needs details
Week 6 | Benjamin Nguyen | Updated the trade prototype JavaScript. Also added the individual reimbursement form, stylesheet, and script. | 2b97aaf, c10a898, c2bc258 | Supported | Provisional
Week 6 | Shayaan M. Dawra | No attributable repository change located for this checkpoint. Confirm any paired work, reviews, testing, or offline work before approving. | History reviewed through 2026-10-25 | Unverified | Needs details
Week 6 | Agah Duzenli | Implemented the Milestone submit-summary JavaScript; updated the Week 6 HTML and state-diagram documentation. | 185dddf, 6b66d12, edb5ca9 | Delivered | Provisional
Week 7 | Austin Tran Nguyen | Added the Week 7 validation and business-rule behavior exercise. | d4804b1 | Delivered | Provisional
Week 7 | Sophia Musetti | No attributable repository change located for this checkpoint. Confirm any paired work, reviews, testing, or offline work before approving. | History reviewed through 2026-10-25 | Unverified | Needs details
Week 7 | Arya Nair | No attributable repository change located for this checkpoint. Confirm any paired work, reviews, testing, or offline work before approving. | History reviewed through 2026-10-25 | Unverified | Needs details
Week 7 | Benjamin Nguyen | Updated the early trade-prototype JavaScript in two commits on October 12. | 79faac0, 929ac10 | Supported | Provisional
Week 7 | Shayaan M. Dawra | No attributable repository change located for this checkpoint. Confirm any paired work, reviews, testing, or offline work before approving. | History reviewed through 2026-10-25 | Unverified | Needs details
Week 7 | Agah Duzenli | Reconciled the rules, workflow, states, dictionary, and tier documentation; introduced the Market-only application screens and decision log. | b69a5c0 | Delivered | Provisional
Week 8 | Austin Tran Nguyen | No attributable repository change located for this checkpoint. Confirm any paired work, reviews, testing, or offline work before approving. | History reviewed through 2026-10-25 | Unverified | Needs details
Week 8 | Sophia Musetti | Added backend validation, six trade tests, and the expected-versus-actual backend test report; removed duplicate backend files. | 4bc65ee, e18fcc3, 945ff01 | Delivered | Provisional
Week 8 | Arya Nair | No attributable repository change located for this checkpoint. Confirm any paired work, reviews, testing, or offline work before approving. | History reviewed through 2026-10-25 | Unverified | Needs details
Week 8 | Benjamin Nguyen | Reordered backend business-rule checks and clarified the matching backend tests. | 62503fe | Supported | Provisional
Week 8 | Shayaan M. Dawra | No attributable repository change located for this checkpoint. Confirm any paired work, reviews, testing, or offline work before approving. | History reviewed through 2026-10-25 | Unverified | Needs details
Week 8 | Agah Duzenli | Added the backend structure and example business logic; placed the application screens in frontend/. | 2ec748a, 1a37cdb | Delivered | Provisional
Week 9 | Austin Tran Nguyen | Corrected outdated application wording and README setup and contribution documentation. | 1f9c3ed | Supported | Provisional
Week 9 | Sophia Musetti | Built the local Express API; connected the trade form with fetch; added API tests, integration results, and screenshot evidence. | 725865f, 14f23c5, 1bccb1e | Delivered | Provisional
Week 9 | Arya Nair | No attributable repository change located for this checkpoint. Confirm any paired work, reviews, testing, or offline work before approving. | History reviewed through 2026-10-25 | Unverified | Needs details
Week 9 | Benjamin Nguyen | No attributable repository change located for this checkpoint. Confirm any paired work, reviews, testing, or offline work before approving. | History reviewed through 2026-10-25 | Unverified | Needs details
Week 9 | Shayaan M. Dawra | No attributable repository change located for this checkpoint. Confirm any paired work, reviews, testing, or offline work before approving. | History reviewed through 2026-10-25 | Unverified | Needs details
Week 9 | Agah Duzenli | No attributable repository change located for this checkpoint. Confirm any paired work, reviews, testing, or offline work before approving. | History reviewed through 2026-10-25 | Unverified | Needs details
Week 10 | Austin Tran Nguyen | Temporary update test | Temporary update test | Delivered | Confirmed
Week 10 | Sophia Musetti | Temporary update test | Temporary update test | Delivered | Confirmed
Week 10 | Arya Nair | Temporary update test | Temporary update test | Delivered | Confirmed
Week 10 | Benjamin Nguyen | Temporary update test | Temporary update test | Delivered | Confirmed
Week 10 | Shayaan M. Dawra | Temporary update test | Temporary update test | Delivered | Confirmed
Week 10 | Agah Duzenli | Temporary update test | Temporary update test | Delivered | Confirmed
Note on D7: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/1211953 https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/4f1d5c4 https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/70cf2d0 Check the commit diff before confirming the assessment.
Note on E7: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D8: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/afe8c13 Check the commit diff before confirming the assessment.
Note on E8: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D9: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/4c4e0da Check the commit diff before confirming the assessment.
Note on E9: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D10: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/ad515aa https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/0cdcf79 Check the commit diff before confirming the assessment.
Note on E10: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D11: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/16b2f64 Check the commit diff before confirming the assessment.
Note on E11: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D12: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/2763615 Check the commit diff before confirming the assessment.
Note on E12: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D13: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/c148e95 https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/39be58c https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/3855c7c Check the commit diff before confirming the assessment.
Note on E13: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D14: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/2ddb1cd https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/ae3598b Check the commit diff before confirming the assessment.
Note on E14: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on E15: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D16: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/8015abe https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/829536b Check the commit diff before confirming the assessment.
Note on E16: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on E17: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D18: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/8081f7d https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/e54acc7 Check the commit diff before confirming the assessment.
Note on E18: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D19: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/9c0ce0f https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/bb499a5 Check the commit diff before confirming the assessment.
Note on E19: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D20: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/e2c55ac https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/401689b Check the commit diff before confirming the assessment.
Note on E20: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D21: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/0856bff https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/2dfd7ac Check the commit diff before confirming the assessment.
Note on E21: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on E22: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on E23: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D24: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/15f1fe1 Check the commit diff before confirming the assessment.
Note on E24: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D25: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/311563c Check the commit diff before confirming the assessment.
Note on E25: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D26: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/5d47986 https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/391308e https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/e988569 Check the commit diff before confirming the assessment.
Note on E26: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on E27: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D28: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/2b97aaf https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/c10a898 https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/c2bc258 Check the commit diff before confirming the assessment.
Note on E28: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on E29: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D30: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/185dddf https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/6b66d12 https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/edb5ca9 Check the commit diff before confirming the assessment.
Note on E30: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D31: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/d4804b1 Check the commit diff before confirming the assessment.
Note on E31: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on E32: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on E33: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D34: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/79faac0 https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/929ac10 Check the commit diff before confirming the assessment.
Note on E34: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on E35: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D36: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/b69a5c0 Check the commit diff before confirming the assessment.
Note on E36: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on E37: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D38: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/4bc65ee https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/e18fcc3 https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/945ff01 Check the commit diff before confirming the assessment.
Note on E38: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on E39: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D40: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/62503fe Check the commit diff before confirming the assessment.
Note on E40: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on E41: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D42: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/2ec748a https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/1a37cdb Check the commit diff before confirming the assessment.
Note on E42: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D43: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/1f9c3ed Check the commit diff before confirming the assessment.
Note on E43: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on D44: Repository evidence: https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/725865f https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/14f23c5 https://github.com/UH-MIS3371/MIS3371-Section10129-Group14/commit/1bccb1e Check the commit diff before confirming the assessment.
Note on E44: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on E45: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on E46: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on E47: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.
Note on E48: Provisional qualitative rating of documented work. Delivered = attributable deliverable; Supported = attributable supporting change; Unverified = contribution needs confirmation. Not a numerical score or course grade.

## Team
The MarketStreet team
Names and roles match the team charter. The Weekly log member dropdown reads this roster.
Member | Primary role | Git author / account aliases
Austin Tran Nguyen | Team Leader / Requirements & Product | AustinNguyen1; Ausnguy; Austin Nguyen
Sophia Musetti | UI / Accessibility | smusetti-star
Arya Nair | Git / Integration | aryanairv
Benjamin Nguyen | Support / Floater | CloudyCloudCloudy; TrueCloudias; Benjamin N
Shayaan M. Dawra | QA / Documentation | Shayaandawra
Agah Duzenli | JavaScript / Logic / Technical Lead | Agah DUZENLI; agahdznl